## Sheet1
# | Date | Issue | Status | Comments
1 | 2021-01-08 | /login when manually entered, app must redirect to dashboard if user is already logged in. | Open | Reopened for new app.
2 | 2021-01-08 | Auto login – Use of cookies | Open | Reopened for new app.
3 | 2021-01-08 | Auto logout | Open | Reopened for new app.
4 | 2021-01-08 | Lazy loading for expenses, dashboard and authentication | Closed | Already done
5 | 2021-01-08 | New expense button should be below | Closed
6 | 2021-01-08 | Angular Material table do not expand in firefox | Closed | Done with css.
7 | 2021-01-08 | Modulerize whole project | Open
8 | 2021-01-10 | In the database there are some blank documents created. | Unable to simulate | Probably due to new expense item created in form but after deletion of the form element may be the document remains created in the backend.
9 | 2021-01-11 | In last six month expense, include current month also | Closed
10 | 2021-01-12 | Remove side effects using ngrx/effects | Open
11 | 2021-01-15 | When app is auto directed to dashboard, results of top six expense graph is not populating. | Closed | Probably while auto routing category is not getting fetched.
12 | 2022-01-13 | Expenses for January not reflecting in the graph | Closed | Updated in the new version, yet to be pushed and deployed. Previous index used for the current month was wrong in two methods.
13 | 2022-01-29 | All data has to be loaded first before rendering the graph of dashboard. | Closed
14 | 2022-01-30 | Authentication of tokens on auto login | Open
15 | 2022-02-14 | StopCurrentMonthExpenseCalculation action is dispatched multiple times. Similarly check for other similar actions/methods. | Closed | StopCurrentMonthExpenseCalculation is getting called because of the observable reference in the dashboard.html
16 | 2022-03-12 | On addition of new expense items, graphs are not reflecting the updated numbers. | Closed | Resolved in new version.
17 | 2023-03-15 | Page rendering for mobile need to be fixed. | Resolved | Chart.js and Apex charts need to be rechecked for fixing the graph in mobile layout. Web and mobile layout for the rest of components has been fixed.
18 | 2023-03-15 | Expense table need to be order by purchase Date | Resolved
19 | 2023-03-16 | Issue in the category expense chart. Maid expense is calculated twice for the month of January. Probably due to the timestamp difference. | Resolved | Timezone added to the aggregation to resolve the issue.
20 | 2023-03-16 | With backend server down during login, error pop up is not coming. Probably with wrong credentials it is coming up. | Open
21 | 2023-03-17 | Validate username and email while signing up an user. | Resolved | Rest should be called when the input field is out of focus. If done on key stroke, there will too many calls.